## Phase 1 — Setup
Phase 1 · Foundation & Setup
Week 1 · 01 Apr – 03 Apr 2026 · 3 Days ·
Task | Owner | Deadline | Status | Notes
Create GitHub repo — project structure, .env.example, README | Backend Eng. | 01 Apr 2026 | Upcoming
Set up Node.js server + Express webhook skeleton | Backend Eng. | 01 Apr 2026 | Upcoming
Configure Twilio Sandbox — join code shared with team & demo users | Soumyadeb | 01 Apr 2026 | Upcoming
Set up ElevenLabs account — Adam voice ID confirmed, API key in .env | Soumyadeb | 02 Apr 2026 | Upcoming
Deploy Railway free tier — permanent HTTPS URL live & shared | Backend Eng. | 02 Apr 2026 | Upcoming
Verify webhook — POST /webhook receives Twilio test ping | Backend Eng. | 03 Apr 2026 | Upcoming
/health endpoint live — returns all service statuses as JSON | Backend Eng. | 03 Apr 2026 | Upcoming
Frontend Eng. reviews demo HTML — confirms it matches WhatsApp UI | Frontend Eng. | 03 Apr 2026 | Upcoming
✓ EXIT CRITERIA: Server is live, Twilio receives messages, all API keys worked sucessfully.
Total Tasks | Completed | In Progress | Upcoming | Phase Status
8 |  |  | 8 | Upcoming

## Phase 2 — Voice
Phase 2 · Voice Pipeline
Week 1–2 · 04 Apr – 08 Apr 2026 · 3 Days · Owner: Backend Eng. + Soumyadeb
Task | Owner | Deadline | Status | Notes
ElevenLabs API call — generate MP3 from text input | Backend Eng. | 04 Apr 2026 | Upcoming
FFmpeg conversion pipeline — MP3 → OGG Opus (WhatsApp voice note codec) | Backend Eng. | 2026-04-06 | Upcoming
Express /audio static route — serve OGG via public HTTPS URL | Backend Eng. | 2026-04-06 | Upcoming
5-minute auto-delete for audio files — prevent storage bloat | Backend Eng. | 06 Apr 2026 | Upcoming
Send first real voice note to WhatsApp — test on iOS | Soumyadeb | 06 Apr 2026 | Upcoming
Test voice note on Android — confirm OGG Opus plays correctly | Frontend Eng. | 07 Apr 2026 | Upcoming
TTS fallback implemented — timeout → italic text message | Backend Eng. | 07 Apr 2026 | Upcoming
Soumyadeb sign-off: deep male voice confirmed, no crashes, both devices | Soumyadeb | 08 Apr 2026 | Upcoming
✓ EXIT CRITERIA: Voice note plays on both iOS and Android. Voice quality is identical to the approved HTML demo.
Total Tasks | Completed | In Progress | Upcoming | Phase Status
8 | 0 | 0 | 8 | Upcoming

## Phase 3 — Bot Engine
Phase 3 · Full Bot Conversation Engine
Week 2–3 · 09 Apr – 14 Apr 2026 · 4 Days ·
Task | Owner | Deadline | Status | Notes
Port state machine to botFlow.js — all 6 stages (idle→profession→product→result→followup) | Backend Eng. | 09 Apr 2026 | Upcoming
Port all financial data to data.js — loans, insurance, investments, credit score | Soumyadeb | 09 Apr 2026 | Upcoming
Flow 1: Greeting + Profession selection (Doctor / CA / Lawyer) | Backend Eng. | 10 Apr 2026 | Upcoming
Flow 2: Loan selection — 4 types, top 3 results per type with voice note | Backend Eng. | 10 Apr 2026 | Upcoming
Flow 3: Insurance plans — full list with voice note | Backend Eng. | 11 Apr 2026 | Upcoming
Flow 4: Investment options — 4 horizons with voice note | Backend Eng. | 11 Apr 2026 | Upcoming
Flow 5: Credit score — 10-digit input, validation, simulated result | Backend Eng. | 2026-04-13 | Upcoming
Follow-up loop — user can explore 3+ topics in one session | Backend Eng. | 2026-04-13 | Upcoming
'hi' / 'hello' resets session cleanly | Backend Eng. | 2026-04-14 | Upcoming
Frontend Eng: validate all text cards & numbered menus on iOS + Android | Frontend Eng. | 2026-04-14 | Upcoming
Soumyadeb: full end-to-end walkthrough of all 5 flows — document gaps | Soumyadeb | 2026-04-15 | Upcoming
✓ EXIT CRITERIA: All 5 flows work end-to-end. Every reply has voice note + text card + menu. No crashes.
Total Tasks | Completed | In Progress | Upcoming | Phase Status
11 | 0 | 0 | 11 | Upcoming

## Phase 4 — QA & Demo
Phase 4 · QA, Testing & Founder Demo
Week 3–4 · 15 Apr – 18 Apr 2026 · 4 Days · Owner: All
Task | Owner | Deadline | Status | Notes
Soumyadeb runs all 11 Acceptance Criteria from BRD — log pass/fail | Soumyadeb | 2026-04-16 | Upcoming
Edge case testing — empty msg, emoji, long text, rapid messages | Soumyadeb | 2026-04-16 | Upcoming
Frontend Eng: QA all cards on 3 devices — iOS, Android, WhatsApp Web | Frontend Eng. | 2026-04-17 | Upcoming
Backend Eng: simulate 20 concurrent users — confirm no crashes | Backend Eng. | 2026-04-17 | Upcoming
Fix all P1 bugs — nothing critical open before demo | Backend Eng. | 2026-04-18 | Upcoming
Soumyadeb prepares Founder demo script — Doctor flow + CA flow | Soumyadeb | 2026-04-18 | Upcoming
Internal dry run — team reviews full demo, timing, talking points | All | 2026-04-17 | Upcoming
FOUNDER DEMO — Live WhatsApp session, Soumyadeb leads | Soumyadeb | 2026-04-18 | Upcoming
✓ EXIT CRITERIA: All 11 acceptance criteria pass. Founder reviews and approves. Change requests logged for Phase 5.
Total Tasks | Completed | In Progress | Upcoming | Phase Status
8 | 0 | 0 | 8 | Upcoming

## Phase 5 — Launch
Phase 5 · Production Launch
Week 4–5 · 21 Apr – 05 May 2026 · 2 Weeks · Owner: All
Task | Owner | Deadline | Status | Notes
Apply for WhatsApp Business Account with Meta — starts Day 1 of project | Soumyadeb | 21 Apr 2026 | Upcoming
Swap Twilio for Meta Cloud API direct — remove per-message markup | Backend Eng. | 21 Apr 2026 | Upcoming
Upgrade ElevenLabs to Starter ($5/mo) — commercial rights active | Soumyadeb | 22 Apr 2026 | Upcoming
Upgrade Railway to paid tier ($5/mo) — production SLA, no sleep | Backend Eng. | 22 Apr 2026 | Upcoming
Replace in-memory session Map with Redis — production reliability | Backend Eng. | 23 Apr 2026 | Upcoming
Set up server monitoring — uptime alerts to Soumyadeb's phone | Backend Eng. | 24 Apr 2026 | Upcoming
Onboard 10 pilot users — Doctors & CAs from F2 Fintech network | Soumyadeb | 28 Apr 2026 | Upcoming
Daily monitoring for first 2 weeks — usage, errors, user feedback | Soumyadeb | Ongoing | Upcoming
Retrospective with Founder — usage data, feedback, Phase 2 proposal | Soumyadeb | 05 May 2026 | Upcoming
✓ EXIT CRITERIA: Bot is live on verified WhatsApp Business number. 10 pilot users active. Zero P1 incidents in first 48 hours.
Total Tasks | Completed | In Progress | Upcoming | Phase Status
9 | 0 | 0 | 9 | Upcoming

## Key Milestones
Key Milestones · F2 Fintech WhatsApp AI Voice Bot
Project Lead: Soumyadeb Dhar · Total: 8 Milestones · Go-Live: 05 May 2026
# | Milestone | Target Date | Owner | Status | Success Criteria
1 | Server live + Twilio connected | 03 Apr 2026 | Backend Eng. | Upcoming | /health returns 200, Twilio ping received
2 | First real voice note plays on WhatsApp | 08 Apr 2026 | Backend Eng. → Soumyadeb | Upcoming | OGG plays on iOS AND Android. Deep male voice confirmed.
3 | All 5 bot flows working end-to-end | 14 Apr 2026 | Full Team → Soumyadeb | Upcoming | Every flow delivers voice note + text card + menu. No crashes.
4 | All QA passed — 11/11 acceptance criteria | 17 Apr 2026 | Soumyadeb + Frontend | Upcoming | BRD AC-01 through AC-11 all marked PASS
5 | FOUNDER DEMO — Live WhatsApp session | 18 Apr 2026 | Soumyadeb (leads) | Upcoming | Founder watches live demo and gives go-ahead for production
6 | Production live — Meta API + Redis + Railway | 24 Apr 2026 | Backend Eng. | Upcoming | Twilio removed. Live on permanent URL. Redis sessions active.
7 | 10 pilot users onboarded | 28 Apr 2026 | Soumyadeb | Upcoming | 10 real users (Doctors/CAs) actively using the bot
8 | GO-LIVE — Official public launch | 05 May 2026 | Soumyadeb → Founder | Upcoming | Verified WA Business number. Zero P1 incidents in 48 hours.
Project Start | Founder Demo | Go-Live Date | Total Duration | Team Size | Monthly Cost
01 April 2026 | 18 April 2026 | 05 May 2026 | 5 Weeks | 3 Members | ₹840 / month

## Responsibility Matrix (hidden)
Responsibility Matrix · Who Does What at Every Phase
R = Responsible · A = Accountable · C = Consulted · I = Informed
PHASE | TASK / ACTIVITY | SOUMYADEB (LEAD) | FRONTEND ENG. | BACKEND ENG.
Phase 1 Setup | Provision all API keys (Twilio, ElevenLabs) | R / A | I | I
| GitHub repo + project structure | A | C | R
| Node.js server + Express webhook skeleton | A | I | R
| Railway deployment + public HTTPS URL | A | I | R
| Team kickoff + alignment on plan | R / A | C | C
Phase 2 Voice | ElevenLabs TTS → MP3 generation | A | I | R
| FFmpeg MP3 → OGG Opus conversion | A | I | R
| Voice note iOS testing + sign-off | R / A | C | I
| Voice note Android testing | C | R | I
| TTS fallback (italic text on failure) | A | I | R
Phase 3 Bot Engine | Port data.js — all financial data | R / A | I | C
| botFlow.js state machine — all 6 stages | A | I | R
| All 5 conversation flows (loan, insurance, invest, credit) | A | C | R
| Session management (in-memory Map) | A | I | R
| Message text formatting + numbered menus | C | R | C
| Visual QA on 3 devices (iOS, Android, WhatsApp Web) | C | R / A | I
| Full flow walkthrough + gap documentation | R / A | C | C
Phase 4 QA & Demo | Run all 11 BRD acceptance criteria | R / A | C | I
| Edge case + stress testing | R | C | A
| Load test — 20 concurrent users | A | I | R
| P1 bug resolution | A | C | R
| Founder demo script preparation | R / A | C | I
| Internal dry run | R / A | R | R
| Live Founder demo — lead & present | R / A | C | C
Phase 5 Launch | WhatsApp Business Account verification with Meta | R / A | I | C
| Twilio → Meta Cloud API migration | A | I | R
| Redis session store implementation | A | I | R
| ElevenLabs + Railway upgrade (paid tiers) | R / A | I | C
| Server monitoring + uptime alerts | A | I | R
| Pilot user onboarding (10 users) | R / A | C | I
| Daily monitoring + feedback collection | R / A | C | C
| Founder retrospective + Phase 2 proposal | R / A | C | I
R / A — Responsible & Accountable (does the work + owns outcome) | R — Responsible (does the work) | A — Accountable (owns the outcome) | C — Consulted (provides input) | I — Informed (kept in the loop)